## SPRINT 1 BACKLOG
SPRINT 1
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
1 | As a user, I would like to see a menu screen so I can navigate through the app easily | M | 2 | • Create menu screen | • Menu should show up when running the program
2 | As a user, I would like there to be a data set so I can access the data I want | M | 1 | • Create data-set | • Data-set should have a required data
3 | As a user, I would like there to be a user interface so I can use the app effectively | M | 1 | • Create user interface | • User interface should show up when running the program
4 | As a user, I would like there to be a database so the data is stored safely and accessable | M | 2 | • Put all data in a PostgreSQL Database | • All data should be in PostgreSQL Database

## SPRINT 2 BACKLOG
SPRINT 2
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
5 | As a user, I would like to have a storyboard so I understand how the app will look and how it will work | S | 1 | • Make a storyboard | • Storyboard clearly shows how our application works
6 | As a user, I would like to see graphs so the data is clearer | M | 3 | • Write code that visualizes data from the database in graphs | • Data turns into the requested graph form
7 | As a user, I would like to be able to compare graphs so I can compare data in a clear way | M | 2 | • Write query that compares data in the database | • Requested data is shown in a way that the user can compare the data
8 | As a user, I would like be able to filter data so I can see only the data that I would like to see | M | 2 | • Write query that filters data in the database | • The user can filter out data that he does not need

## SPRINT 3 BACKLOG
SPRINT 2
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
9 | As a user, I would like to see the data appear on a map so I can see where the data belongs | M | 2 | • Link data with locations on the map | • Requested data appears on a map at the right location
10 | As a user, I would like to see the mapp in the app so I can see the locations | M | 2 | • Write code that displays map in app | • The map appears in the app with
11 | As a user, I would like there to be a home, back and start buttons so I can navigate through the app easily | M | 1 | • Create buttons: home, back, start | • The home, back, start buttons appear and function correctly.