## SPRINT 1 BACKLOG
SPRINT 1
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
0 | As a player, I want to have a main menu, so I can choose what to do from there. | M | 1 | • Create a main menu | • Main menu should show up, when running the program
1 | As a player, I want to be able to start the game from the main menu or change settings of the game. | M | 1 | • Add a start, options, rules, highscore and exit button to the main menu | • Have clickable buttons on the main menu • Have multiple buttons on the main menu
2 | As a player, I want to be able to read the rules, so that I know how to play the game | M | 1 | • Add a rules button on the main menu | • Show the rules after clicking the rule button

## SPRINT 2 BACKLOG
SPRINT 2
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
5 | Storyboard | S | 1 | • Make a storyboard | • Storyboard clearly shows how our application works
6 | Create functions that turn data into graphs | M | 2 | • Create functions that turn data into graphs | • Data turns into the requested graph form
7 | Create funtions to compare data | M | 2 | • Create functions to compare data | • Requested data is shown in a way that the user can compare the data
8 | Create function to filter data | M | 2 | • Create function to filter data | • The user can filter out data that he does not need