## Blad1
Projectnaam | User story # | Work item # | 07-04 - Remaining Hours | 10-04 Remaining Hours | 11-04 Remaining Hours | 12-04 Remaining Hours
Sprint 2 | User story 5 | Work item 5 | 1 | 0 | 0 | 0
Sprint 2 | User story 6 | Work item 6 | 3 | 2 | 1 | 0
Sprint 2 | User story 7 | Work item 7 | 2 | 2 | 1 | 0
Sprint 2 | User story 8 | Work item 8 | 2 | 2 | 1 | 0
|  | Ideal | 8 | 5.333 | 2.666 | 0
|  | Actual | 8 | 6 | 3 | 0