## Blad1
Projectnaam | User story # | Work item # | 14-04 - Remaining Hours | 17-04 Remaining Hours | 18-04 Remaining Hours | 19-04 Remaining Hours
Sprint 3 | User story 9 | Work item 9 | 2 | 0 | 0 | 0
Sprint 3 | User story 10 | Work item 10 | 2 | 2 | 1 | 0
Sprint 3 | User story 11 | Work item 11 | 1 | 1 | 1 | 0
|  | Ideal | 5 | 3.333 | 1.666 | 0
|  | Actual | 5 | 3 | 2 | 0